ABRO DIGITAL LLC

Master Implementation Guide

This guide consolidates every decision, workflow, and action item from all planning sessions into a single, ordered checklist. Follow it phase by phase. Do not skip ahead.

| HOW TO USE | Work through each phase in order. Complete every checked box before moving to the next phase. Phases 0 and 1 must be done before any product goes live. Phases 2+ can be done in parallel once products are earning. |
| --- | --- |

| Phase 0 Foundation | Phase 1 First Product | Phase 2 Content Engine | Phase 3 Growth | Phase 4 Scale | Open Gaps Still Needed |
| --- | --- | --- | --- | --- | --- |

# Phase 0: Foundation

Complete everything in this phase before importing a single workflow. These are the non-negotiables.

## 0A. Legal Structure

Form the LLC before generating revenue. You need it to open Mercury Bank and connect platforms properly.

| □ | Northwest Registered Agent: Go to northwestregisteredagent.com. Select Wyoming LLC. $139 formation + $60/yr. Takes 1-2 business days. |
| --- | --- |
| □ | Download LLC documents: Save: Articles of Organization, Operating Agreement, Registered Agent agreement. |
| □ | IRS EIN — call at 7 PM Malaysia time: Call +1-267-941-1099 (6 AM US Eastern). Say: "I am applying for an EIN for a single-member LLC formed in Wyoming." Takes 20 min. Write down EIN immediately. |
| □ | Apply for Mercury Bank: mercury.com — needs LLC cert + EIN. Takes 3-5 days. Primary USD account. |
| □ | Apply for Airwallex: airwallex.com — Wise replacement. Needs LLC cert + EIN. 2-5 days. USD/MYR/PKR. |
| □ | Open Payoneer personal: Open now before LLC is ready. Connects to Gumroad immediately. Backup withdrawal channel. |
| □ | Apply for PayPal Business: Secondary only. Use for Payhip. Never hold >$200 here. |
| □ | Hire CPA (Malaysia or Pakistan): Annual filing: Form 1120 + 5472. $25,000/form penalty if missed. Budget $400-600/yr. |

## 0B. VPS Infrastructure

n8n is already running. These are the remaining packages and configurations needed before workflows function.

Run these commands on your Contabo VPS:

# PDF generation
apt-get install -y wkhtmltopdf poppler-utils fonts-dejavu-core
# Mockup generation
pip3 install Pillow --break-system-packages
# Cloud storage (for PDFs + mockups)
curl https://rclone.org/install.sh | sudo bash
rclone config   # add remote: name=r2, type=s3, provider=Cloudflare
# Speech synthesis (for WF09B)
apt-get install -y espeak-ng ffmpeg
# Piper TTS binary: https://github.com/rhasspy/piper/releases

| □ | Cloudflare R2 bucket: Create free account at cloudflare.com. Add R2. Create bucket: clearstack-products. Enable public access. Copy Account ID. |
| --- | --- |
| □ | Update rclone config: Replace YOUR_R2_ACCOUNT_ID in WF02C and WF13 with real Cloudflare Account ID. |
| □ | VPS backup cron: Follow SECURITY_CREDENTIALS_FIX.md — backup script + Backblaze B2. Takes 30 min. ~$0/month under 10GB. |
| □ | /tmp cleanup cron: Follow SECURITY_CREDENTIALS_FIX.md — one cron line. Prevents disk fill from PDF/video temp files. |
| □ | Move credentials to n8n: Follow SECURITY_CREDENTIALS_FIX.md — 2-3 hrs. WordPress, Brevo, Etsy, Gumroad, Telegram, ElevenLabs. |
| □ | UFW firewall: ufw allow 22,80,443. ufw allow 5678 from YOUR_IP only. ufw enable. |
| □ | Fail2ban: apt-get install fail2ban. Protects SSH from brute force. |

## 0C. Legal Documents (WordPress)

Required before any EU traffic hits your site. GDPR violations start at €20,000.

| □ | Privacy Policy: Generate at privacypolicygenerator.info. Install as WordPress page. Link in footer. |
| --- | --- |
| □ | Terms of Service: Same generator. Required for e-commerce. Link in footer. |
| □ | Refund Policy: Digital goods: no refunds after download. State this clearly. Link from every product page. |
| □ | Digital Product License: Personal use only. No resale. No redistribution. One buyer, one license. Create as WP page. |
| □ | Cookie Consent plugin: Install CookieYes (free) or Complianz on WordPress. GDPR required for Google Analytics. |
| □ | DMCA Policy: Generate at dmca.com/free. Install as WordPress page. Needed to file takedowns if templates copied. |

# Phase 1: First Product Live

Import workflows in this exact order. Test each one manually before connecting to the next.

## 1A. Import Workflow Order

| ID | NAME | TRIGGER | STATUS |
| --- | --- | --- | --- |
| WF06 | Brand Config | Manual — run once to populate | IMPORT |
| WF07 | Halal Guardian | Called by WF02B on every product | IMPORT |
| WF01 | Research Agent | Scheduled: Monday 9 AM | IMPORT |
| WF02B | Product Creation Factory | Webhook from WF01 | IMPORT |
| WF02C | PDF Generation Pipeline | Webhook from WF02B | IMPORT |
| WF13 | Mockup Generator | Webhook from WF02C | IMPORT |
| WF03 | Publishing Agent | Webhook from WF13 | IMPORT |

Before importing each workflow: open the JSON, search for YOUR_ and update every placeholder value.

Placeholders to replace in every workflow:

- YOUR_GOOGLE_SHEET_ID_HERE

- YOUR_N8N_BASE_URL

- YOUR_R2_ACCOUNT_ID

- YOUR_WORDPRESS_URL

- YOUR_ETSY_API_KEY

- YOUR_TELEGRAM_BOT_TOKEN

- YOUR_TELEGRAM_CHAT_ID

## 1B. WF06 Configuration Checklist

WF06 is the brain of the system. Every other workflow reads from it. Fill it completely before running anything else.

| □ | brand.name: ClearStack Studio |
| --- | --- |
| □ | brand.website: Your WordPress URL |
| □ | legal.company_name: Abro Digital LLC |
| □ | legal.ein: Your EIN from IRS call |
| □ | banking.mercury_routing: From Mercury Bank dashboard after approval |
| □ | banking.mercury_account: From Mercury Bank dashboard |
| □ | platforms.etsy_api_key: From Etsy developer portal |
| □ | platforms.gumroad_token: From Gumroad Settings > Applications |
| □ | platforms.ayrshare_key: From Ayrshare dashboard |
| □ | platforms.brevo_api_key: From Brevo Settings > API Keys |
| □ | ai.ollama_base_url: http://localhost:11434 (confirm Ollama is running) |
| □ | brand_voice: Copy short_version from BRAND_VOICE_CLEARSTACK.json |

## 1C. Manual Test Sequence

Run each test manually and verify the output before enabling automated triggers.

| □ | Test WF01: Trigger manually. Wait 5-10 min. Check Google Sheet: did research results appear? |
| --- | --- |
| □ | Test WF02B: Copy one row from WF01 output. Post to WF02B webhook manually. Check output: title, description, tags all present? |
| □ | Test WF07: WF02B calls this automatically. Check that halal_approved: true appears in output. |
| □ | Test WF02C: Post WF02B output to WF02C webhook. Wait 10-20 min. Check R2 bucket: did PDF appear? Open it. Is it printable? |
| □ | Test WF13: Post WF02C output to WF13 webhook. Wait 2-3 min. Check R2 bucket: did 5-6 PNG mockups appear? Open them. Do they look professional? |
| □ | Test WF03 (Gumroad only first): Post WF13 output to WF03. Set publish_to: ["gumroad"] only. Check Gumroad: did product appear with correct title, description, price, and PDF file? |
| □ | Review live product: Open the Gumroad product page. Would you buy this? Fix anything that looks wrong before enabling Etsy. |
| □ | Enable Etsy in WF03: Add "etsy" to publish_to array. Run full pipeline again with a second product. |

## 1D. Etsy Account Setup

| □ | Create Etsy seller account: Use business email. Shop name: ClearStack Studio. Country: Malaysia. |
| --- | --- |
| □ | Etsy payment setup: Connect Mercury Bank account after it is approved. |
| □ | Shop policies: Use your Refund Policy and License Terms. Copy exact text. |
| □ | Listing velocity limit: Do not publish more than 5 listings per day for the first 30 days. WF03 has a rate limit flag — enable it. |
| □ | Star Seller target: Respond to all messages within 24 hrs. 95%+ 5-star reviews. 95%+ on-time dispatch. $300+ in 3 months. |

# Phase 2: Content Engine

Start Phase 2 after 5 products are live on Etsy and Gumroad. These workflows drive traffic to products that already exist.

## 2A. WordPress Setup

| □ | Install WordPress: On your VPS or a separate hosting. Point clearstackstudio.com to it. |
| --- | --- |
| □ | Install Yoast SEO: Configure: set canonical URLs, enable XML sitemap, connect to Google Search Console. |
| □ | Install Elementor or GeneratePress: Clean, fast theme. No page builder bloat. |
| □ | Install CookieYes: GDPR cookie consent. Required before analytics go live. |
| □ | Create static pages: Home, About, Shop (redirect to Gumroad), Blog, Contact, Privacy, ToS, Refund, License. |
| □ | Submit to Google Search Console: Add property. Submit sitemap (yoursite.com/sitemap_index.xml). |
| □ | Install Umami Analytics: Self-hosted on your VPS. Free. GDPR compliant. No cookies. Guide: umami.is/docs |

## 2B. Content Workflows

| ID | NAME | TRIGGER | STATUS |
| --- | --- | --- | --- |
| WF09A | Blog + Carousel Engine | Webhook from WF03 after product publishes | IMPORT |
| WF09C | Blog Publisher | Webhook from WF09A | IMPORT |
| WF10A | Internal Linking Agent | Daily 2 AM | IMPORT |
| WF10B | WordPress Health Monitor | Daily 6 AM | IMPORT |
| WF12A | Schema Injector | Daily 3 AM | IMPORT |
| WF12C | AI Overview Optimizer | Weekly Sunday 8 AM | IMPORT |

What these produce per product:

- 1 blog post (SEO optimized, schema injected, AI overview ready)

- 3 carousels (Instagram, LinkedIn, Pinterest)

- Internal links updated across all existing posts

- WordPress health check — email digest if anything breaks

## 2C. Email Engine

| ID | NAME | TRIGGER | STATUS |
| --- | --- | --- | --- |
| WF11A | Email Sequence Writer | Webhook — called on new subscriber | IMPORT |
| WF11B | Brevo Automation Builder | Webhook from WF11A | IMPORT |
| WF11C | Newsletter Scheduler | Thursday 9 AM | IMPORT |

| □ | Create Brevo account: brevo.com — free tier: 300 emails/day, unlimited contacts. |
| --- | --- |
| □ | Create 4 contact lists: Welcome (new subscribers), Customers (buyers), Lead Magnet, Newsletter. |
| □ | Create email capture form: On WordPress: offer a free lead magnet. Connect form to Brevo Welcome list. |
| □ | Patch WF03: Add post-purchase trigger to send buyer email to WF11A with sequence_type: post_purchase. |
| □ | Test welcome sequence: Subscribe with a test email. Confirm 6 emails arrive over 7 days. |
| □ | Test post-purchase sequence: Buy your own product on Gumroad. Confirm 5 post-purchase emails arrive. |

## 2D. Social Media Accounts

18 accounts across 6 niches. Warm them manually before enabling WF04 automation.

Warming schedule per account:

- Week 1: Create account. Complete profile (bio, avatar, link). Follow 20-30 relevant accounts. Like/comment 10 posts per day. No automation.

- Week 2: Post 1 piece of content manually. Continue engagement. Still no automation.

- Week 3+: Enable WF04. Start with 1 post/day. Increase gradually.

| RISK | 18 accounts from one VPS IP posting simultaneously = mass ban. Use a residential proxy or rotate IPs. Ayrshare manages posting but each account needs a unique device/session fingerprint for platform safety. |
| --- | --- |

## 2E. Video Engine (Optional — Phase 2)

| ID | NAME | TRIGGER | STATUS |
| --- | --- | --- | --- |
| WF09B | Video Engine | Webhook from WF09A | IMPORT |
| WF04 | Social Media Agent | Webhook from WF09B | IMPORT |

| □ | Install Piper TTS: github.com/rhasspy/piper/releases. Place binary at /usr/local/bin/piper. |
| --- | --- |
| □ | Download voice model: en_US-lessac-medium.onnx — best quality free voice. |
| □ | Test WF09B manually: Post one product to webhook. Confirm 4 videos are created and uploaded to R2. |
| □ | Connect WF04: Enable Ayrshare connection. Test with 1 platform first (YouTube Shorts). |
| □ | Activate remaining platforms: Add TikTok, Instagram Reels, Facebook Reels after YouTube test passes. |

# Phase 3: Growth

Start Phase 3 when you have 20+ products live and at least 1 sale. These workflows scale what is already working.

## 3A. SEO Scale

| ID | NAME | TRIGGER | STATUS |
| --- | --- | --- | --- |
| WF12B | Programmatic SEO | Manual — run once, then weekly | IMPORT |
| WF05 | Humanization Agent | Called by WF12B on every page | IMPORT |

WF12B generates 200 programmatic SEO pages (20 audiences x 10 product types). Run in batches of 5 with 5-minute gaps. Total processing: ~8 hours.

| □ | Import WF12B: Set batch_size: 5. Set batch_delay_minutes: 5. Run during off-peak hours (2-6 AM). |
| --- | --- |
| □ | Monitor GSC after 4 weeks: Check Google Search Console for indexing status. Target: 50%+ of pages indexed within 6 weeks. |
| □ | Import WF05: Humanization agent runs after WF12B. Makes AI content pass originality checks. |

## 3B. ManyChat (Social Lead Capture)

Activate when 50+ followers on any account OR when you have a lead magnet ready.

| □ | Create ManyChat account: manychat.com — free tier: 1000 contacts. |
| --- | --- |
| □ | Build Comment-to-Link flow: Use MANYCHAT_PHASE2_BLUEPRINT.md — complete flow provided. |
| □ | Build Welcome New Follower flow: Same guide. Auto-sends lead magnet to new followers. |
| □ | Build Lead Magnet Delivery flow: Delivers free product via DM. Collects email. |
| □ | Connect ManyChat to n8n: Webhook: ManyChat captures email → posts to n8n → WF11A starts welcome sequence. |
| □ | Test full flow: Comment on your own post. Confirm: DM sent → email captured → welcome email arrives. |

## 3C. WooCommerce (Phase 2 Activation)

WooCommerce is already configured in WF06 but disabled. Activate when any ONE of these triggers is met:

- 20+ products sold

- 200+ email subscribers

- 500+ monthly blog visitors

- Etsy fees exceed $50/month

To activate: In WF06, change woocommerce.enabled from false to true. That is the only code change needed. WF03 will start publishing to WooCommerce automatically.

## 3D. KDP Books

| ID | NAME | TRIGGER | STATUS |
| --- | --- | --- | --- |
| WF08A | KDP Book Factory | Manual trigger — run per book | IMPORT |
| WF08B | Book Publisher | Webhook from WF08A | IMPORT |

KDP (Kindle Direct Publishing) allows publishing low-content books (planners, journals, notebooks) to Amazon. Same products as Etsy but different format and audience. Revenue share: 60% royalty.

| □ | Create KDP account: kdp.amazon.com — connect to Mercury Bank for royalty payments. |
| --- | --- |
| □ | Import WF08A + WF08B: See KDP_SETUP_GUIDE.md for full configuration. |
| □ | Test with 1 book: Run WF08A manually for one planner. Review generated book files before publishing. |

# Phase 4: Scale

Start Phase 4 when revenue exceeds $500/month consistently. These are investment decisions, not setup tasks.

## 4A. Second Brand: NurturePrint

| □ | Register DBA: File DBA "NurturePrint" under Abro Digital LLC in Wyoming. ~$50. |
| --- | --- |
| □ | Target niche: Health & Longevity + Personal Finance. Different audience from ClearStack. |
| □ | Platform focus: Teachers Pay Teachers (educational content). Pinterest (health content). |
| □ | Create 10 products: Run same WF01-WF13 pipeline. Different niche config in WF06. |

## 4B. MySQL + Laravel Migration

When product catalog exceeds 500 items, Google Sheets will slow down. Migrate to MySQL.

| □ | Provision MySQL on VPS: apt-get install mysql-server. Create database: abro_digital. |
| --- | --- |
| □ | Create tables: products, listings, sales, analytics, email_subscribers, social_accounts. |
| □ | Build Laravel app: New repo: abro-digital-api. Replaces heavy Google Sheets read/write in all workflows. |
| □ | Update n8n workflows: Replace Google Sheets nodes with HTTP Request nodes pointing to Laravel API. |

## 4C. UAE Freezone LLC (Optional)

Evaluate if annual revenue exceeds $30,000. UAE Freezone offers 0% corporate tax and easier banking.

| □ | Research Freezone options: Sharjah Media City (Shams): ~$1,500/yr. Dubai South: ~$2,000/yr. |
| --- | --- |
| □ | Consult CPA: Compare Wyoming LLC ongoing costs vs UAE Freezone. Make data-driven decision. |
| □ | Migration plan: Transfer brand assets and contracts from Abro Digital LLC to new entity. |

# Open Gaps: Still Need Building

These were identified in the audit but not yet built. Prioritize by phase.

## Build Before First Product (Blockers)

| TASK | STATUS | FILE / ACTION | PRIORITY |
| --- | --- | --- | --- |
| Etsy velocity throttle in WF03 | OPEN | Add rate limiter: max 5/day | BLOCKER |
| Privacy Policy on WordPress | OPEN | privacypolicygenerator.info | BLOCKER |
| Terms of Service on WordPress | OPEN | privacypolicygenerator.info | BLOCKER |
| Refund Policy on WordPress | OPEN | Digital goods: no refund text | BLOCKER |
| Digital Product License page | OPEN | Personal use only text | BLOCKER |
| Cookie consent plugin | OPEN | Install CookieYes | BLOCKER |

## Build in Month 1 (High Value)

| TASK | STATUS | FILE / ACTION | PRIORITY |
| --- | --- | --- | --- |
| Unified dashboard (Telegram) | OPEN | WF14 — /status command | HIGH |
| Etsy auto-responder | OPEN | WF15 — replies within 30min | HIGH |
| Product performance feedback to WF01 | OPEN | Sales data → niche scoring | HIGH |
| Win-back email sequence | OPEN | Finish WF11A prompt | HIGH |
| Umami analytics on VPS | OPEN | Self-hosted, GDPR safe | HIGH |
| Seasonal campaign calendar | OPEN | Inject into WF01 context | HIGH |
| DECISIONS.md file | OPEN | Create in Git repo manually | HIGH |
| Workflow Git export | OPEN | Weekly cron: n8n export → Git | HIGH |

## Build in Month 2 (Growth)

| TASK | STATUS | FILE / ACTION | PRIORITY |
| --- | --- | --- | --- |
| SSL expiry check in WF10B | OPEN | Add to health monitor | MED |
| Docker health checks in WF10B | OPEN | Container status alerts | MED |
| Ollama context length guards | OPEN | Truncate long inputs | MED |
| Etsy listing refresh (30-day) | OPEN | Update top 10 listings monthly | MED |
| Content repurposing to Reddit/Quora | OPEN | Blog → Reddit summary workflow | MED |
| Notion Template Gallery in WF03 | OPEN | Add free platform, 30M users | MED |
| Open WebUI for Ollama testing | OPEN | Docker container, local only | LOW |
| Portainer for Docker management | OPEN | Visual container management | LOW |

# Workflow Index

Every workflow file in the /outputs/digital-empire-workflows/ folder.

| ID | NAME | TRIGGER | STATUS |
| --- | --- | --- | --- |
| WF01 | Research Agent | Monday 9 AM (scheduled) | READY |
| WF02 | Creation Agent (v1 — superseded) | Legacy | SKIP |
| WF02B | Product Creation Factory | Webhook from WF01 | READY |
| WF02C | PDF Generation Pipeline | Webhook from WF02B | READY |
| WF03 | Publishing Agent | Webhook from WF13 | READY |
| WF04 | Social Media Agent | Webhook from WF09B | READY |
| WF05 | Humanization Agent | Called by WF12B | READY |
| WF06 | Brand Config | Manual (run once) | READY |
| WF07 | Halal Guardian | Called by WF02B | READY |
| WF08A | KDP Book Factory | Manual trigger | READY |
| WF08B | Book Publisher | Webhook from WF08A | READY |
| WF09A | Content Engine (Blog + Carousel) | Webhook from WF03 | READY |
| WF09B | Video Engine | Webhook from WF09A | READY |
| WF09C | Blog Publisher | Webhook from WF09A | READY |
| WF10A | Internal Linking Agent | Daily 2 AM | READY |
| WF10B | WordPress Health Monitor | Daily 6 AM | READY |
| WF11A | Email Sequence Writer | Webhook (subscriber/buyer) | READY |
| WF11B | Brevo Automation Builder | Webhook from WF11A | READY |
| WF11C | Newsletter Scheduler | Thursday 9 AM | READY |
| WF12A | Schema Injector | Daily 3 AM | READY |
| WF12B | Programmatic SEO (200 pages) | Manual (batched) | READY |
| WF12C | AI Overview Optimizer | Weekly Sunday 8 AM | READY |
| WF13 | Mockup Generator | Webhook from WF02C | READY |
| WF14 | Unified Dashboard + /status | Telegram command | OPEN |
| WF15 | Etsy Auto-Responder | Etsy webhook on new message | OPEN |

## Support Documents

| ABRO_DIGITAL_LLC_FORMATION.md | Step-by-step LLC formation and banking setup |
| --- | --- |
| BRAND_VOICE_CLEARSTACK.json | Inject into every AI system prompt via WF06 |
| SECURITY_CREDENTIALS_FIX.md | Credentials to n8n + VPS backup + /tmp cleanup |
| GAP_AUDIT_STATUS.md | Master list of all 53 gaps and their current status |
| MANYCHAT_PHASE2_BLUEPRINT.md | Complete ManyChat flow blueprints for 4 flows |
| WOOCOMMERCE_PHASE2_GUIDE.md | WooCommerce activation instructions |
| EMAIL_AI_SEO_SETUP_GUIDE.md | Brevo setup + AI SEO workflow configuration |
| ARCHITECTURE_V2.md | Full system architecture diagram and data flow |
| 09A_SETUP_GUIDE.md | Content engine setup instructions |
| 09B_SETUP_GUIDE.md | Video engine setup: Piper TTS + FFmpeg |
| 08_KDP_SETUP_GUIDE.md | KDP account setup and book format requirements |

The Only Metric That Matters

Products live on Etsy and Gumroad. Count them. Everything else is infrastructure.